## Blatt1
Time Schedule - Semesterthesis - Julian Surber - HS2015
Supervisor: Margarita Chli, Lucas Pinto Teixeira
| 20.10. | 27.10. | 3.11. | 10.11. | 17.11. | 24.11. | 01.12. | 08.12.
| 1.5 days | 3 days | 3 days | 3 days | 3 days | 3days | 3 days | 0 days
Literature Reading
Define Performance Measures
Define desired plots for thesis
ROVIO performance: Experiments, Limitations, Comparisons
OCVIS performance: Experiments (make it work!), Limitations, Comparisons
Writing
Presentation preparation
Milestone 1: Codes working, Calibration, Desired plots defined, Datasets defined, Postprocessing ready
Milestone 2: Thesis first version (for review)
Milestone 3: Presentation
Milestone 4: Thesis final version